Prayer Retreat Prep Plan

Day Away - Steps to Freedom in Christ

3 Months Out- Reserve Location and schedule with others who will be a part of that day. 		              PRAY for/over location and place.

6 Weeks Out – Begin to promote and mention it in class. Have video or in class testimonies.

Check Supply of Steps Books. Order what is needed.

4 Weeks Out- Send out email to all former class participants who may want to sign up. Begin to 		            pray over these names.

3 Weeks Out- Have a signup sheet in class (OR email out google form sign up)

Encourage them to read sections in the book on steps (pp. 130-144).

2 Weeks Out – Double check meeting space. Make sure room setup has been communicated.

    - Arrange childcare as needed.

    - Organize refreshments.

    - Email out to the team that will facilitate steps and make sure everyone knows their assignments.

1 Week Out- Communicate Names of attendees and retreat facilitators to prayer team asking that they not be kept from attending by the enemy.

- Email to all attendings letting them know what to bring and what to expect.

- Gather Steps Books, Supplemental Docs, Red/Green Cards, Sound System

- Consider Fasting for a meal or day leading up to the event.

Day Before Event – Be in Prayer

- Schedule place of our kids to be in a safe Spiritual environment. Make sure they are with godly people.

- Consider Fasting One Meal

- Don’t plan anything too stressful or strenuous.

- Make personal lunch plans in advance for Sunday.

Day of Event

    - Remain in an attitude of dependent prayer.

    - Arrive an hour ahead of the others.

    - Confirm Rooms are set up.

    - Sign in Table ready.

    - Set up refreshments.

    - Put out Signs to create a safe environment for people coming in.

      - Pray Over the Room and Individual Rooms

      - Other facilitators should be encouraged to pray while others are leading their steps. On Steps 3 & 6 the team should pray together while others are in their individual rooms.

    - Greet and Assign Rooms

    - Write Steps and/or Phone Numbers on the White Board

Following Week.

- Send Follow up email, encouraging them with next steps.

- (Prayers, Who I am Statements, Truth Statements, Stronghold busting)

- Link to Neil’s Devotionals ficm.org/Neils-blogs/ or FIC Couse App

- Encourage them to invite a friend to the next course offering (Provide them the start date (month is fine)

- Asking them what God Showed them and feedback on how we could create a better experience (Longer time, More time alone, less this, more that)